## Project Plan
|  | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6
Design
Schema Definitions
REST API Endpoint Definitions
Order Flow Design
Store Onboarding Process Design
Menu Items Publishing Process Design
Architecture Documentation
Environment Setup
Infra : Create build, test and linting scripts and configs
Identify primary package dependencies
CI/CD
Marketplace Core Services Development
Inventory
Payment
Cart
Order
Transaction
Doordash Marketplace Integration
Store Locations Setup / Upload
API Development / Webhook Integration
Sandbox Integration Testing
Live Store Catalog Upload
Go Live
Google Marketplace Integration
Tax
Catolog
Store App Integration
LID
Cancelation
Customer profile
Testing

## Doordash Plan
7NOW Marketplace Development |  | Start Date | End Date | Estimated Days
|  | 2019-09-05 | 2019-12-05 | 91
1 | Design | 2019-09-05 | 2019-09-19 | 14
1.1 | Schema Definitions | 2019-09-05 | 2019-09-10 | 3
1.2 | REST API Endpoint Definitions | 2019-09-05 | 2019-09-10 | 3
1.3 | Publish API Specs and Schema | 2019-09-11 | 2019-09-13 | 2
1.4 | Architecture | 2019-09-14 | 2019-09-17 | 2
1.5 | Order Flow Design | 2019-09-14 | 2019-09-17 | 2
1.6 | Store Onboarding Process Design | 2019-09-14 | 2019-09-17 | 2
1.7 | Menu Items Publishing Process Design | 2019-09-14 | 2019-09-17 | 2
1.8 | 7NOW API Enhancements for Marketplace | 2019-09-17 | 2019-09-19 | 2
1.9 | 7NOW Store App Enhancements | 2019-09-17 | 2019-09-19 | 2
2 | Environment Setup | 2019-09-17 | 2019-09-27 | 10
2.1 | Code : Project Setup | 2019-09-17 | 2019-09-19 | 2
2.1 | Code : Create build, test and linting scripts and configs | 2019-09-17 | 2019-09-20 | 3
2.1 | Cloud : Infrastructure Setup | 2019-09-17 | 2019-09-27 | 8
2.1 | Cloud : CI/CD Setup | 2019-09-17 | 2019-09-27 | 8
3 | Marketplace Core Services Development | 2019-09-20 | 2019-10-04 | 14
3.1 | Order Service | 2019-09-20 | 2019-09-27 | 5
3.2 | Catalog Service | 2019-09-20 | 2019-09-27 | 5
3.3 | Store Service | 2019-09-20 | 2019-09-27 | 5
3.4 | Tax Service | 2019-09-28 | 2019-10-03 | 4
3.5 | Payment Service | 2019-09-28 | 2019-10-04 | 5
4 | 7NOW API - Marketplace Support Developments | 2019-10-04 | 2019-10-30 | 20
4.1 | 7NOW <=> Marketplace Events Bridge | 2019-10-04 | 2019-10-11 | 5
4.2 | Marketplace Order Special Handling | 2019-10-04 | 2019-10-11 | 5
4.3 | ISP Transaction Service Updates | 2019-10-04 | 2019-10-11 | 5
4.4 | 7NOW Store App Changes | 2019-10-12 | 2019-10-18 | 5
4.5 | 7NOW & Marketplace Integration Testing | 2019-10-18 | 2019-10-30 | 8
5 | Doordash - Marketplace Integration | 2019-10-31 | 2019-11-15 | 15
5.1 | Store Online / Offline Setup | 2019-10-31 | 2019-11-06 | 4
5.2 | Catalog Items Synchronization Process Development | 2019-10-31 | 2019-11-12 | 8
5.3 | Order Checkout + Tax | 2019-10-31 | 2019-11-07 | 5
5.4 | Order Placement | 2019-10-31 | 2019-11-07 | 5
5.5 | Post Order Placement Events Handling | 2019-11-08 | 2019-11-15 | 5
5.6 | Order Cancelation Handling | 2019-11-08 | 2019-11-13 | 3
5.7 | Webhook Integration | 2019-11-08 | 2019-11-14 | 4
6 | Full End-to-End Testing | 2019-11-16 | 2019-11-29 | 10
7 | Preparations to Go Live | 2019-11-16 | 2019-12-03 | 17
7.1 | Production Environment Setup | 2019-11-16 | 2019-11-22 | 5
7.2 | CI/CD updates for Production Environment | 2019-11-16 | 2019-11-19 | 2
7.3 | Marketplace API / Services Release | 2019-11-20 | 2019-11-22 | 2
7.4 | 7NOW API Enhancements Release | 2019-11-20 | 2019-11-25 | 3
7.5 | Internal Testing in Production | 2019-11-26 | 2019-12-03 | 5
8 | Go Live | 2019-12-04 | 2019-12-05 | 1
Formulas:
Start Date = [Start Date, row below]
Start Date = [Start Date, row above]
End Date = MAX([End Date, row below]:D11)
End Date = WORKDAY([Start Date],[Estimated Days])